## ProductBacklog
PRODUCT BACKLOG
|  |  | Batch 2018_2019 | Free Time Shopping
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
SB1 | US1 | Admin | Managing all the sign's up done by the user | Admin have a record of all the sign's up done by the user
SB1 | US2 | Admin | Managing all the login's done by the user | Admin have a record of all the login's done by the user
SB1 | US3 | Admin | Manages the database for the logined users | Admin can manage the data
SB1 | US4 | Admin | Manage the forget password option for the users | Admin can manage the forget password option
SB1 | US5 | Admin | Sends a confirmation mail when a user sign's up | Admin can send a confirmation mail when any user sign's up
SB1 | US6 | Admin | Won't let a user to login until he confirms the signed up login id | Admin will check for that the user has confirmed the email id or not
SB1 | US7 | Admin | Check the number users online on the website | Admin can check the number users online
SB1 | US8 | Admin | Check the number of hits on the website | Admin can check the number of hits
SB1 | US9 | Admin | Manage the password options | Admin can manage password options
SB1 | US10 | Admin | Manage the inventory panel for the website | Admin can manage the inventory panel for the website
SB1 | US11 | Admin | Add new items in the inventory database | Admin can add new items in the inventory database
SB1 | US12 | Admin | Delete the unused or unpopular items from the database | Admin can delete the unused or unpopular items
SB1 | US13 | Admin | Manage the discounts given on each items | Admin can manage the discounts given
SB1 | US14 | Admin | Check if there are more than one active seession of a user | Admin can check if there are more than one active seession of a user
SB1 | US15 | Admin | Delete the suspicious accounts | Admin can delete any suspicious account
SB1 | US16 | Admin | Delete accounts of users who post false information | Admin can delete accounts of users who post false information
SB1 | US17 | Admin | Delete the accouts of users who post nudity | Admin can delete the accouts of users if anything is imprompt
SB1 | US18 | Admin | Check the profit generated each month | Admin can check the profit generated each month
SB1 | US19 | Admin | Stocking of new items on the website | Admin can stock new items
SB1 | US20 | Admin | Deletion of the items which will not be available anymore | Admin can delete the items which will not be available anymore
SB1 | US21 | Admin | Managing all the filters for shopping on the website | Admin can manage all the filters for shopping
SB1 | US22 | Admin | Manage the sorting option for shopping | Admin can manage the sorting option for shopping
SB1 | US23 | Admin | Manage each users shopping cart | Admin can manage each users shopping cart
SB1 | US24 | Admin | Address of each user should be auto read whenever placing a new order | Address of each user can be auto read
SB1 | US25 | Admin | Sending OTP for the payment gateway for netbanking and card payments | Admin can send otp for the payment gateway for netbanking
SB2 | US26 | Admin | Cash on Delivery option will be managed according to the users need | Admin can manage the cash on delivery option
SB2 | US27 | Admin | The product needs to be managed which a user wants to sell | Admin can manage the products which the users are selling
SB2 | US28 | Admin | All the details should be proper when a user is selling any product | Admin should check that all the information added by the user against the product is correct
SB2 | US29 | Admin | All the comments will be coming to the Admin panel | Admin should check all the comments added by the users
SB2 | US30 | Admin | All the queries asked by the users needs to be managed by the Admin | Admin can check and manage all the queries
SB2 | US31 | Admin | All the queries needs to be answered through the Admin Panel | Admin needs to answer all the queries
SB2 | US32 | Admin | All the answers to the queries will reach the user through email | Admin should answer the query of any user through email
SB2 | US33 | Admin | Can check and edit anything in the comments section | Admin can check and edit any comment
SB2 | US34 | Admin | Can manage the interface given for the users | Admin can manage the interface of the website
SB2 | US35 | Admin | Can delete any item from the website | Admin can delete any item from the website
SB2 | US36 | Admin | Can add any item on the website | Admin can add any item on the website
SB2 | US37 | Admin | Can make edit the description for the website | Admin can make edit the description of the website
SB2 | US38 | Admin | Contact section will be managed by the Admin Panel | Admin can manage the contact sectionon the website
SB2 | US39 | Admin | Can add new developers which are helping the Admin team | Admin can add new developers
SB2 | US40 | Admin | Meet the team panel needs to be managed by the Admin | Admin can manage meet the team panel on the website
SB2 | US41 | Admin | Security of the website | Admin can control the security of the website
SB2 | US42 | Admin | Supports the forget password option | Admin can support the forget password option
SB2 | US43 | Admin | Cares for the site | Admin can take care of the website
SB2 | US44 | Admin | Provides a wishlist option to all the users | Admin can provide a wishlist option to the users
SB2 | US45 | Admin | Provides an option to add innumerable things in the wishlist | Admin can provide an option to add innumerable things in the wishlist
SB2 | US46 | Admin | Can remove any item from any users wishlist which is out of stock | Admin can remove any item from any users wishlist which is put of stock
SB2 | US47 | Admin | Need to take care that the website does not get hacked by anyone | Admin needs to take care that the website does not get hacked
SB2 | US48 | Admin | Needs to check that the user is getting the order in the delivery dates | Admin needs to check that the user is getting the order in the delivery dates
SB2 | US49 | Admin | Needs to figure the problem if the user is not receiving the order in time | Admin needs to figure the problem if the user is not receiving the order in time
SB2 | US50 | Admin | Can update the prices of any item | Admin can update the prices of any items
SB3 | US51 | User | Can Sign Up if new to the website | User can sign up if new on the website
SB3 | US52 | User | Should provide with the correct personal information to sign up | User should provide with the correct personal information
SB3 | US53 | User | Should confirm the email ID from the confirmation email sent | User should confirm the email id through the confirmation mail
SB3 | US54 | User | Now the new user can check all the items present on the website | User can check all the items present on the website
SB3 | US55 | User | Can login if is a existing user | User can login if is an existing user
SB3 | US56 | User | Can check all the items present on the website | User can check all the items present on the website
SB3 | US57 | User | Can Purchase any item from the website | User can purchase any item from the website
SB3 | US58 | User | Can sell any item on the website | User can sell any item on the website
SB3 | US59 | User | Users can comment on all the items which they have/not purchased from the website | User can comment on all the items which they have/not purchased
SB3 | US60 | User | Users can buy innumerable items from the website | User can buy innumerable items from the website
SB3 | US61 | User | Users can sell innumerable items on the website | User can sell innumerable items on the website
SB3 | US62 | User | Users can save many items on the website in the wishlist | User can save many items on the website in the wishlist panel
SB3 | US63 | User | Users can give feedback for the website | User can give feedback for the website
SB3 | US64 | User | Users can ask put any query in the Query section | User can ask put any query in the query section
SB3 | US65 | User | Users will get the answers to their queries through email | User will get the answers to their queries through email
SB3 | US66 | User | Users need to provide all the information about the item they need to sell | User need to provide all the information about the item they need to sell
SB3 | US67 | User | Users can buy all the items present on the website | User can buy all the items present on the website
SB3 | US68 | User | Users will have the benefits of all the discounts availing on the website | User will have the benefits of all the discounts availing on the website
SB3 | US69 | User | Users will have the benefit of the wishlist option | User will have the benefit of the wishlist option
SB3 | US70 | User | FAQ will help the users to get answers to there questions easily | User will get the answers to their queries through FAQ section easily
SB3 | US71 | User | Users can ask questions in the FAQ sections | User can ask questions in FAQ section as well
SB3 | US72 | User | Users can buy any item from the website | User can buy any item from the website
SB3 | US73 | User | Users can do the payment for the order according to their wish | User can do the payment for the order according to their wish
SB3 | US74 | User | Users can choose pay on delivery option | User can choose pay on delivery option for any product
SB3 | US75 | User | Users can choose net banking payment gateway | User can choose net banking payment gateway
SB4 | US76 | User | Users can choose card payment gateway | User can choose card payment gateway to do the payments
SB4 | US77 | User | Users can exchange the purchased product | User can exchange the purchased product
SB4 | US78 | User | Users can return the purchased product | User can return the purchased product
SB4 | US79 | User | To get the refund, users need to provide their account details | User get the refund, but for that users need to provide their account details
SB4 | US80 | User | To exchange users can buy any piece from the same product | User can exchange can but another piece from the same product
SB4 | US81 | User | If a user forgets the password for their account they can change it | User can change the password if they forget the password
SB4 | US82 | User | Security question will help the user to change their password with this option | User can reset the password with the help of the security question
SB4 | US83 | User | User can check all the options related to product | User can check all the options realted to the product
SB4 | US84 | User | User can filter the options to buy according to their wish | User can filter the options to buy according to their wish
SB4 | US85 | User | User can cancel the order according to their wish | User can cancel the order the order according to their wish
SB4 | US86 | User | User uploads a item which they want to sell needs to be shipped by the user only | User uploads a item which they want to sell needs to be shipped by the user only
SB4 | US87 | User | User can use the contact us option to ask for any query | User can use the contact us option to ask for any query
SB4 | US88 | User | User can upload their profile picture | User can upload their profile picture
SB4 | US89 | User | User can change their personal information | User can change their personal information
SB4 | US90 | User | User can change their mobile number | User can change their mobile number
SB4 | US91 | User | User can add multiple address | User can add multiple address
SB4 | US92 | User | User can check their order history | User can check their order history
SB4 | US93 | User | User ask as many questions as they want | User ask as many questions as they want
SB4 | US94 | User | If the user is selling any product and the buyer does not like the product the user need to get back the order | User have to take back the product if not product selled by the user
SB4 | US95 | User | User can delete their account from the admin panel | User can delete their account
SB4 | US96 | User | Users can not check any others account | User cannot check any others account
SB4 | US97 | User | Users can not delete their comment once done | User can not delete their comment once done
SB4 | US98 | User | Users can not delete their question once asked in FAQ section | User can not delete their question once asked in FAQ section
SB4 | US99 | User | User can check the about option in the website | User can check the about option on the website
SB4 | US100 | User | User can check the meet the team option | User can check the meet the team option on the website

## SprintBacklog1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Free Time Shopping>
SB1/US1 | Can check the website | SB3/D1/T1 | make the front hand page | SS+VV | completed | 2018-09-01
|  | SB1/D1/T2 | front hand development | SS+VV | completed | 2018-09-01
|  | SB1/D1/T3 | Validation | ST+SS | completed | 2018-09-01
|  | SB1/D1/T4 | design login page | SS+VV | completed | 2018-09-01
|  | SB1/D1/T5 | design sign up page | SS | completed | 2018-09-01
SB1/US2 | Can shop any product | SB1/D2/T1 | design Add to Cart | SS+VV | completed | 2018-09-01
|  | SB1/D2/T2 | design the product functionality feature | ST | completed | 2018-09-01
|  | SB1/D2/T3 | Design the buy now page and connect with databases | SS+VV | completed | 2018-09-01
|  | SB1/D2/T4 | Add zoom features | SS | completed | 2018-09-01
SB1/US3 | Can make queries | SB1/D3/T1 | design the Frequently ask questions | SS+VV | completed | 2018-09-02
|  | SB1/D3/T2 | connect with the databases | VV | completed | 2018-09-02
|  | SB1/D3/T3 | connect with the Admin | SS+VV | completed | 2018-09-02
|  | SB1/D3/T4 | Add the email functionality | VV | completed | 2018-09-02
|  | SB1/D3/T5 | Reply functionality in the admin | SS+VV | completed | 2018-09-02
SB1/US4 | Can make comments | SB1/D4/T1 | Design the front hand of the | ST | completed | 2018-09-02
|  | SB1/D4/T2 | connect with the databases | SS+VV | completed | 2018-09-02
|  | SB1/D4/T3 | notifications functionality in the comment | ST | completed | 2018-09-02
|  | SB1/D4/T4 | reply functionalityin the comment | SS+VV | completed | 2018-09-02
SB1/US5 | Can sign up if not a existing user | SB1/D5/T1+C24:C28 | design the front hand of the sign up page | ST | completed | 2018-09-03
|  | SB1/D5/T2 | validation | SS+VV | completed | 2018-09-03
|  | SB1/D5/T3 | connect with databases | SS+VV | completed | 2018-09-03
|  | SB1/D5/T4 | Add the confirmations functionality with the mail | SS+VV | completed | 2018-09-03
|  | SB1/D5/T5 | exiting account | SS+VV | completed | 2018-09-03
SB1/US6 | USER can comment and ask queries in FAQ | SB1/D5/T1 | design the front develeopment | SS | completed | 2018-09-04
|  | SB1/D5/T2 | connect with databases | VV | completed | 2018-09-04
|  | SB1/D5/T3 | send all the comment to other user | SS | completed | 2018-09-04
|  | SB1/D5/T4 | All the mail features in the FAQ | VV+SS | completed | 2018-09-04
SB1/US7 | Should confirm the new account with the confirmation mail | SB1/D5/T1 | Connect with the databases | VV | completed | 2018-09-05
|  | SB1/D5/T2 | confirm the mail through SMTP | VV+SS | completed | 2018-09-05
|  | SB1/D5/T3 | Send the request | SS | completed | 2018-09-05
|  | SB1/D5/T4 | Login the page with the confirmations | SS | completed | 2018-09-05
SB1/US8 | Should enter a existing email id | SB1/D5/T1 | design the front hand development | VV+VV | completed | 2018-09-06
|  | SB1/D5/T2 | connect with databases | ST | completed | 2018-09-06
|  | SB1/D5/T3 | chech whether user exist or not | SS+VV | completed | 2018-09-06
SB1/US9 | Should enter the actual details | SB1/D5/T1 | front hand development | VV | completed | 2018-09-06
|  | SB1/D5/T2 | connect with databases | VV | completed | 2018-09-06
|  | SB1/D5/T3 | chech whether user exist or not | VV | completed | 2018-09-07
|  | SB1/D5/T4 | send the notifications through the email | SS | completed | 2018-09-07
SB1/US10 | Can check the order history | SB1/D5/T1 | front hand development | SS | completed | 2018-09-07
|  | SB1/D5/T2 | connect with the databases | SS | completed | 2018-09-07
|  | SB1/D5/T3 | apply the select query | SS | completed | 2018-09-07
|  | SB1/D5/T4 | maintained the session to the user | SS | completed | 2018-09-07
|  | SB1/D5/T5 | send the notifications through the email | VV | completed | 2018-09-08
SB1/US11 | Can change profile picture | SB1/D5/T1 | front hand development | VV | completed | 2018-09-08
|  | SB1/D5/T2 | connect with databases | VV | completed | 2018-09-08
|  | SB1/D5/T3 | send message succesfully change | VV | completed | 2018-09-08
SB1/US12 | Can update the address and phone numbers | SB1/D5/T1 | front hand development | VV | completed | 2018-09-08
|  | SB1/D5/T2 | connect with the databases | VV+SS | completed | 2018-09-08
|  | SB1/D5/T3 | update the all the informations | VV+SS | completed | 2018-09-08
SB1/US13 | Should recofirm the email id if changing | SB1/D5/T1 | front hand development | VV | completed | 2018-10-09
|  | SB1/D5/T2 | connect with databases | ST | completed | 2018-10-09
|  | SB1/D5/T3 | connect with the smtp server | VV | completed | 2018-10-09
|  | SB1/D5/T4 | send the mail to the mail | SS+ST | completed | 2018-10-09
SB1/US14 | Password can be changed as many times as required | SB1/D5/T1 | front hand development | SS+ST | completed | 2018-10-09
|  | SB1/D5/T2 | connect with the databases | VV | completed | 2018-10-09
|  | SB1/D5/T3 | Apply updations in the password | VV | completed | 2018-10-10
|  | SB1/D5/T4 | Asses the Account with the new password | VV | completed | 2018-10-10
SB1/US15 | New password can be entered through the profile settings | SB1/D5/T1 | front hand development | VV | completed | 2018-10-10
|  | SB1/D5/T2 | connect with databases | VV | completed | 2018-10-10
|  | SB1/D5/T3 | update the all the informations | VV | completed | 2018-10-10
SB1/US16 | Should remember the security question regarding password | SB1/D5/T1 | front hand development | VV+SS | completed | 2018-10-11
|  | SB1/D5/T2 | connect with databases | VV+SS | completed | 2018-10-11
|  | SB1/D5/T3 | Add Admin feature through the email | SS | completed | 2018-10-11
|  | SB1/D5/T4 | Add the feature if forget the security questions | SS | completed | 2018-10-11
|  | SB1/D5/T5 | Add the Ask the Admin with the email | SS | completed | 2018-10-11
SB1/US17 | Can comment on any product | SB1/D5/T1 | front hand development | SS+VV | completed | 2018-10-12
|  | SB1/D5/T2 | connect with databases | VV | completed | 2018-10-12
|  | SB1/D5/T3 | Add feature on every product | ST | completed | 2018-10-12
|  | SB1/D5/T4 | send the notifications through the email | ST | completed | 2018-10-13
SB1/US18 | Can ask any query | SB1/D5/T1 | front hand development | SS | completed | 2018-10-13
|  | SB1/D5/T2 | connect with smtp sever | SS+ST | completed | 2018-10-14
|  | SB1/D5/T3 | Add the FAQ | SS | completed | 2018-10-14
SB1/US20 | Can ask query regarding products | SB1/D5/T1 | front hand development | VV+SS | completed | 2018-10-14
|  | SB1/D5/2 | connect with databases | SS+VV | completed | 2018-10-15
|  | SB1/D5/3 | send the email | VV | completed | 2018-10-15
SB1/US21 | Will receive answers through email id for the query | SB1/D5/T1 | send the mail | SS | completed | 2018-10-16
|  | SB1/D5/T2 | connect with the databases | VV | completed | 2018-10-17
|  | SB1/D5/T3 | connect with the smtp server | SS+VV | completed | 2018-10-18

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 23 | 0 | Tasks
2018-09-12 | 42 | 0
2018-09-11 | 38 | 0
2018-09-14 | 5 | 0
2018-09-16 | 5 | 0
2018-09-18 | 3 | 0
Days

## SpritBacklog2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Free Time Shopping>
SB2/US1 | Can buy innumerable products | SB2/D1/T1 | front hand development | SS+VV | completed | 2018-09-19
|  | SB2/D1/T2 | connect with the databses | ST | completed | 2018-09-19
|  | SB2/D1/T3 | apply the updation query | SS | completed | 2018-09-19
|  | SB2/D1/T4 | add the rating feature on the product | SS+VV | completed | 2018-09-19
|  | SB2/D1/T5 | add the add to cart | VV | completed | 2018-09-19
SB2/US2 | Can buy products according to likes | SB2/D2/T1 | front end development | VV | completed | 2018-09-19
|  | SB2/D2/T2 | connect with the databses | SS+VV | completed | 2018-09-19
|  | SB2/D2/T3 | add the rating feature | ST | completed | 2018-09-19
|  | SB2/D2/T4 | add the comments on the ecvery product | SS+VV | completed | 2018-09-20
SB2/US3 | Can sell products which are in a good condition | SB2/D3/T1 | front hand development | ST | completed | 2018-09-20
|  | SB2/D3/T2 | connect with the databses | SS+VV | completed | 2018-09-20
|  | SB2/D3/T3 | Add the feature of sell the product | VV | completed | 2018-09-20
|  | SB2/D3/T4 | add the upload feature | SS | completed | 2018-09-20
|  | SB2/D3/T5 | that product connect with the other user | SS | completed | 2018-09-20
SB2/US4 | Should set the right amount for selling a product | SB2/D4/T1 | front hand development | SS | completed | 2018-09-20
|  | SB2/D4/T2 | connect with the databses | SS+VV | completed | 2018-09-21
|  | SB2/D4/T3 | send notifications to the user of the updated amount | VV | completed | 2018-09-21
|  | SB2/D4/T4 | connect with the smtp server | ST | completed | 2018-09-22
SB2/US5 | Should take care of the security of there account | SB2/D5/T1 | front hand development | SS+VV | completed | 2018-09-22
|  | SB2/D5/T2 | connect with the databses | ST | completed | 2018-09-22
|  | SB2/D5/T3 | connect with the smtp server | ST | completed | 2018-09-22
|  | SB2/D5/T4 | confirm the mail and apply the updation query | VV | completed | 2018-09-22
SB2/US6 | Should keep a strong password | SB2/D5/T1 | front hand development | SS | completed | 2018-09-16
|  | SB2/D5/T2 | connect with the databses | VV | completed | 2018-09-16
|  | SB2/D5/T3 | convert the message in the encyption from | SS+VV | completed | 2018-09-18
|  | SB2/D5/T4 | disble ctrl+s key | VV | completed | 2018-09-19
|  | SB2/D5/T5 | disble right click | VV | completed | 2018-09-21
SB2/US7 | Should remember the security question | SB2/D5/T1 | front hand development | VV | completed | 2018-09-21
|  | SB2/D5/T2 | connect with the databses | VV | completed | 2018-09-21
|  | SB2/D5/T3 | add feature if in case user forget the sq and sa | SS | completed | 2018-09-22
|  | SB2/D5/T4 | add the mail feature in the security feature | SS | completed | 2018-09-25
|  | SB2/D5/T5 | connect with the smtp server | SS | completed | 2018-09-25
SB2/US8 | Payments can be made offline through pay on delivery | SB2/D5/T1 | front hand development | SS | completed | 2018-09-25
|  | SB2/D5/T2 | connect with the databses | VV | completed | 2018-09-25
|  | SB2/D5/T3 | add feature of the paytm number | VV | completed | 2018-09-25
|  | SB2/D5/T4 | cash on delivery | VV+ST | completed | 2018-09-25
SB2/US9 | Payments can be made online | SB2/D5/T1 | add the net banking functionality | VV | completed | 2018-09-29
|  | SB2/D5/T2 | add the paytm functionality | ST | completed | 2018-09-29
|  | SB2/D5/T3 | add the cash on the delivery | ST | completed | 2018-09-29
|  | SB2/D5/T4 | connect with the databses | VV | completed | 2018-09-29
|  | SB2/D5/T5 | front hand development | VV | completed | 2018-09-30
SB2/US10 | Can check for discounts and offers | SB2/D5/T1 | front hand development | VV | completed | 2018-09-30
|  | SB2/D5/T2 | connect with the databses | VV | completed | 2018-09-29
|  | SB2/D5/T3 | send notifications to the user of the updated amount | SS+ST | completed | 2018-10-05
|  | SB2/D5/T4 | send notifications of the discount through the email | SS+VV | completed | 2018-10-05
|  | SB2/D5/T5 | connect with the smtp server | VV+SS | completed | 2018-09-29
SB2/US11 | Can check newly added products | SB2/D5/T1 | front hand development | VV+SS | completed | 2018-10-10
|  | SB2/D5/T2 | connect with the databases | VV+SS | completed | 2018-10-10
|  | SB2/D5/T3 | connect with smtp server | VV | completed | 2018-10-10
|  | SB2/D5/T4 | send the notifications to the user newly add product by email | VV | completed | 2018-10-10
SB2/US12 | Can use filter to buy product according to requirement | SB2/D5/T1 | front hand development | SS | completed | 2018-10-10
|  | SB2/D5/T2 | connect with the databases | ST | completed | 2018-10-10
|  | SB2/D5/T3 | add the filter options | SS+ST | completed | 2018-10-10
|  | SB2/D5/T4 | add the serch options in the product | SS | completed | 2018-10-10
|  | SB2/D5/T5 | send the notifications to the user newly add product by email | SS | completed | 2018-10-10
SB2/US13 | Can sort the products according to prices/new/relevance | SB2/D5/T1 | front hand development | SS | completed | 2018-10-11
|  | SB2/D5/T2 | connect with the databases | VV | completed | 2018-10-11
|  | SB2/D5/T3 | Add the sorting feature | VV | completed | 2018-10-11
|  | SB2/D5/T4 | add the smtp server | VV | completed | 2018-10-11
SB2/US14 | Product can be exchanged if needed | SB2/D5/T1 | front hand development | VV | completed | 2018-10-11
|  | SB2/D5/T2 | connect with the databses | VV | completed | 2018-10-11
|  | SB2/D5/T3 | add the exchange policy | SS+VV | completed | 2018-10-11
|  | SB2/D5/T4 | add the money returned module | VV+SS | completed | 2018-10-11
|  | SB2/D5/T5 | connect with the smtp server | SS | completed | 2018-10-11
SB2/US15 | Product can be returned if needed | SB2/D5/T1 | front hand development | SS+ST | completed | 2018-10-11
|  | SB2/D5/T2 | connect with the databses | ST | completed | 2018-10-15
|  | SB2/D5/T3 | add the exchange policy | VV+ST+SS | completed | 2018-10-15
|  | SB2/D5/T4 | add the money returned module | VV+SS | completed | 2018-10-15
|  | SB2/D5/T5 | connect with the smtp server | SS+VV | completed | 2018-10-15
SB2/US16 | Payments for the return order will be received on bank accounts | SB2/D5/T1 | front hand development | SS+VV | completed | 2018-10-15
|  | SB2/D5/T2 | connect with the databses | SS+VV | completed | 2018-10-15
|  | SB2/D5/T3 | add the exchange policy | SS+VV | completed | 2018-10-15
|  | SB2/D5/T4 | add the money returned module | ST | completed | 2018-10-15
|  | SB2/D5/T5 | connect with the smtp server | VV | completed | 2018-10-15
SB2/US17 | Product should be under the exchange and return option | SB2/D5/T1 | front hand development | VV | completed | 2018-10-15
|  | SB2/D5/T2 | connect with the databses | VV | completed | 2018-10-15
|  | SB2/D5/T3 | add the exchange policy | VV | completed | 2018-10-15
|  | SB2/D5/T4 | add the money returned module | SS | completed | 2018-10-15
|  | SB2/D5/T5 | connect with the smtp server | SS | completed | 2018-10-22

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Free Time Shopping>
SB3/US1 | Managing all the sign's up done by the user. | SB3/D1/T1 | Creating the signup form frontend | SS+VV | completed | 2018-10-23
|  | SB3/D1/T2 | Making the front end responsive | SS+VV+ST | completed | 2018-10-23
|  | SB3/D1/T3 | Creating the signup database where the user info will be stored | SS+VV+ST | completed | 2018-10-23
|  | SB3/D1/T4 | Implementing Email confirmation facility in signup form | SS+VV+ST | completed | 2018-10-23
|  | SB3/D1/T5 | Managing the signup insert query | SS+VV | completed | 2018-10-23
|  | SB3/D1/T6 | Testing if the signup and queries are working or not | VV | completed | 2018-10-23
SB3/US2 | Check the number of hits on the website and manage inventory | SB3/D2/T1 | Implementing the script to log the hits | ST | completed | 2018-10-24
|  | SB3/D2/T2 | Testing the script | SS+VV+ST | completed | 2018-10-24
|  | SB3/D2/T3 | Manage the inventory panel for the website | SS+VV | completed | 2018-10-24
|  | SB3/D2/T4 | Connecting the GUI with backend scripts | SS+VV | completed | 2018-10-24
|  | SB3/D2/T5 | Delete the unused or unpopular items from the database | ST+VV | completed | 2018-10-24
SB3/US3 | Admin will check for that the user has confirmed the email id or not | SB3/D3/T1 | After signing up the user have received the confirmation mail or not | SS+VV | completed | 2018-10-24
|  | SB3/D3/T2 | Implement the malier script | ST+SS+VV | completed | 2018-10-24
|  | SB3/D3/T3 | Test the script for mailing | SS | completed | 2018-10-24
|  | SB3/D3/T4 | Connect the script with signup form | VV+ST | completed | 2018-10-24
SB3/US4 | Making th contact us form | SB3/D4/T1 | All the comments will be coming to the Admin panel | VV | completed | 2018-10-26
|  | SB3/D4/T2 | Create the contact form UI | ST | completed | 2018-10-26
|  | SB3/D4/T3 | Writing the queries and the script to handel information | ST+SS | completed | 2018-10-26
|  | SB3/D4/T4 | Testing the script | VV+SS | completed | 2018-10-26
SB3/US5 | Admin can manage the details of the products. | SB3/D5/T1 | Making script to remove any item from any users wishlist which is out of stock | VV | completed | 2018-10-26
|  | SB3/D5/T2 | Generating the UI of admin panel | SS+ST | completed | 2018-10-26
|  | SB3/D5/T3 | Connecting the admin dahboard with the backend script | ST | completed | 2018-10-27
|  | SB3/D5/T4 | Fetch the data from the database to be shown on the UI | VV+ST | completed | 2018-10-27
SB3/US6 | Admin can manage the sessions | SB3/D6/T1 | Implement the session management script in backend | VV | completed | 2018-10-27
|  | SB3/D6/T2 | Checking if there are more than one active sessions for a user | SS+ST | completed | 2018-10-27
|  | SB3/D6/T3 | writing the session termination code | ST | completed | 2018-10-27
|  | SB3/D6/T4 | Testing the script for session termination | VV+ST | completed | 2018-10-27
SB3/US7 | Admin can perform CRUD operations on the database | SB3/D6/T1 | Making the SELECT,UPDATE,INSERT and DELETE functionality | VV | completed | 2018-10-27
|  | SB3/D6/T2 | Implementing the functionality on the admin dashboard | SS+ST | completed | 2018-10-27
|  | SB3/D6/T3 | Testign the CRUD functionality on database | ST | completed | 2018-10-27
|  | SB3/D6/T4 | Refelecting the changes onto the UI | VV+ST | completed | 2018-10-27
SB3/US8 | Admin can check the number of users on line | SB3/D6/T1 | Adding the user on line functionality | VV | completed | 2018-10-27
|  | SB3/D6/T2 | Increment the counter when a user logs in | SS+ST | completed | 2018-10-27
|  | SB3/D6/T3 | Get the number of users | ST | completed | 2018-10-29
|  | SB3/D6/T4 | Refelecting the changes onto the UI | VV+ST | completed | 2018-10-29
SB3/US9 | Admin can check the number of users on line | SB3/D6/T1 | Adding the user on line functionality | VV | completed | 2018-10-29
|  | SB3/D6/T2 | Increment the counter when a user logs in | SS+ST | completed | 2018-10-29
|  | SB3/D6/T3 | Get the number of users | ST | completed | 2018-10-29
|  | SB3/D6/T4 | Refelecting the changes onto the UI | VV+ST | completed | 2018-10-29

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Free Time Shopping>
[5 empty] | pending | 2019-01-01
SB4/US1 | Can manage the filter option for shopping | SB4/D1/T1 | Can manage the filter option for shopping | SS+VV | pending | 2019-01-01
|  | SB4/D1/T2 | Add the filter feature | SS | pending | 2019-01-01
|  | SB4/D1/T3 | Integrate the filter script with the UI | VV | pending | 2019-01-01
|  | SB4/D1/T4 | Reflect changes in UI | ST+VV | pending | 2019-01-01
SB4/US2 | ADMIN can Delete the suspicious accounts | SB4/D2/T1 | Check for no active users or suspcious accounts | VV+ST+SS | pending | 2019-01-01
|  | SB4/D2/T2 | Add the delete account feature | VV | pending | 2019-01-01
|  | SB4/D2/T3 | Delete accounts of users who post false information from database | ST+VV | pending | 2019-01-01
|  | SB4/D2/T4 | Delete the accouts of users who post nudity | SS | pending | 2019-01-01
SB4/US3 | ADMIN Can check all the orders made by the users | SB4/D3/T1 | Develop the UI where admin can see the orders | SS+ST | pending | 2019-01-02
|  | SB4/D3/T2 | Fetch data from database to show on UI | VV+ST | pending | 2019-01-02
|  | SB4/D3/T3 | Manages the paid/unpaid orders | SS | pending | 2019-01-02
|  | SB4/D3/T4 | Checks for that the order is delivered or not | VV | pending | 2019-01-02
|  | SB4/D3/T5 | Manages for the exchange/return option | SS+VV | pending | 2019-01-02
SB4/US4 | ADMIN manages all the payments made | SB4/D4/T1 | All the payments are done properly or not | SS+ST | pending | 2019-01-02
|  | SB4/D4/T2 | Integrate the third party payment script | VV+ST | pending | 2019-01-02
|  | SB4/D4/T3 | log the payment info in the database | ST | pending | 2019-01-02
|  | SB4/D4/T4 | Notify on UI if transaction is successful | SS | pending | 2019-01-02
SB4/US5 | ADMIN checks for the status of the website | SB4/D5/T1 | Checks for the profits made from the website | VV+SS | pending | 2019-01-03
|  | SB4/D5/T2 | Integrate third party js script for statistics | ST | pending | 2019-01-03
|  | SB4/D5/T3 | Checks for the number of visits each day | SS | pending | 2019-01-03
|  | SB4/D5/T4 | Checks if there is no traffic on the website | SS | pending | 2019-01-03
SB4/US6 | Security of the website | SB4/D5/T1 | look around for vulnerabilities | VV+SS | pending | 2019-01-04
|  | SB4/D5/T2 | Protect from DDOS attack | ST | pending | 2019-01-05
|  | SB4/D5/T3 | Protect from SQL injection | SS | pending | 2019-01-06
|  | SB4/D5/T4 | Protect from XSS attack | SS | pending | 2019-01-07
SB4/US7 | All the queries asked by the users needs to be managed by the Admin | SB4/D5/T1 | Develop the UI | VV+SS | pending | 2019-01-10
|  | SB4/D5/T2 | Develop a questioning responding system | ST | pending | 2019-01-10
|  | SB4/D5/T3 | Show questions on UI | SS | pending | 2019-01-10
|  | SB4/D5/T4 | Provide the statistics of answered questions | SS | pending | 2019-01-11

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)